**Planning Health Informatics Context project**

Context Text Teaching Assistants (CP TAs)

1. Dwi Hartanto (cahsantan@gmail.com) VR thuisbehandeling sociale fobie
2. Corine Horsch ([corinehorsch@gmail.com](mailto:corinehorsch@gmail.com)) Thuisbehandeling slaap stoornis
3. Wenxin Wang (wangwxzy@gmail.com) Thuismanagement nierpatiënten

Software Engineering Teaching Assistant (SE TA)

??

|  |  |  |
| --- | --- | --- |
| Week | Datum | Activiteit |
| Q3.1 | 11/2 – 15/2 | Seminar  Vrijdag 15 Feb 2013 13:45-17:45, EWI gebouw - Timmanzaal LB01.170   * 13:45 - 14:30 Willem-Paul Brinkman, TU Delft, *Introductie Health Informatics - Virtual eCoaching* * 14:45 – 15:30 Céline van Lint, LUMC, *Disease Management Systeem (DMS) voor nierpatiënten* * 15:45 – 16:30 Corine Horsch, TU Delft, *Sleep Care eCoaching* * 16:45 – 17:30 Dwi Hartanto, TU Delft, *Home-based virtual reality therapy* |
| Q3.2 | 18/2 – 22/2 | Seminar  Vrijdag 22 Feb 2013 13:45-17:45, EWI gebouw - Timmanzaal LB01.170   * 13:45 - 14:30 Isabel Kampmann, Universiteit van Amsterdam, Sociale fobie en virtual reality exposure therapie * 14:45 – 15:30: Robbert-Jan Beun, Univesiteit van Utrecht, *Slaap problemen en geautomatiseerde therapieën* * 15:45 – 16:30: Olivier Blanson Henkemans, TNO, *eCoaching* * 16:45 – 17:30: Wenxin Wang, TU Delft, *Thuismanagement systeem voor van nierpatiënten*   Practicum   * Woensdag 20 Feb 2013 15:30 DW-PC 0.010 Indeling groepen en toekenning onderwerp (SE&CP TAs) |
| Q3.3 | 25/2 – 1/3 | Seminar  Woensdag 27 Feb 2013 13:45 - 14:30, EWI gebouw - Snijderszaal LB01.010   * 13:45 - 14:30 : Dwi Hartanto, TU Delft, *virtual characters*   Practicum  Vrijdag 13:45 – 14:45 DW-PC 0.010 voortgangsbespreking met groepen (Brinkman, SE&CP TAs) |
| Q3.4 | 4/3 – 8/3 | Practicum  Vrijdag 13:45 – 14:45 DW-PC 0.010 voortgangsbespreking met groepen (SE&CP TAs)  Deadline:   * Submit: draft initial Product Vision and Planning (8/3) |
| Q3.5 | 11/3 - 15/3 | Practicum  Vrijdag 13:45 – 14:45 DW-PC 0.010 voortgangsbespreking met groepen (Brinkman, SE&CP TAs)  Deadline:   1. Submit: initial Product Vision and Planning (15/3) 2. Submit: first version of Emergent Architectural Design (15/3) 3. Submit: first Scrum Plan (15/3) |
| Q3.6 | 18/3 – 22/3 | Deadline:   * Submit: draft Context Seminar Report (22/3) |
| Q3.7 | 25/3 - 29/3 |  |
| Q3.8 | 1/4 – 5/4 | Deadline:   1. Submit: final Context Seminar Report (5/4) 2. Submit: first Peer-Review (Q3/W8) |

|  |  |  |
| --- | --- | --- |
| Week | Datum | Activiteit |
| Q4.1 | 22/4 - 26/4 |  |
| Q4.2 | 29/4 – 3/5 | Practicum  Vrijdag 10:00-12:00 Room ??? Product demo door de groepen (Brinkman, SE&CP TAs)  Deadline:   1. product demo 2. Submit: draft Emergent Architecture design (for feedback) 3. upload source code for first evaluation by SIG |
| Q4.3 | 6/5 – 10/5 |  |
| Q4.4 | 13/5 – 17/5 |  |
| Q4.5 | 20/5 – 25/5 |  |
| Q4.6 | 27/5 – 31/5 | Practicum  Vrijdag 10:00-11:00 DW-PC 0.010 voortgangsbespreking met groepen (Brinkman, SE&CP TAs)  Deadline:   1. Submit: draft Product Vision and Planning 2. Submit: draft Emergent Architecture Design 3. Submit: draft Report and Product |
| Q4.7 | 3/6 – 7/6 |  |
| Q4.8 | 10/6 – 14/6 | Deadline:   1. Submit: second Peer-Review (Q4/W8) 2. submit: final Product Vision and Planning 3. submit: final Emergent Architecture Design 4. submit: final Report and Product 5. upload source code for final evaluation by SIG |
| Q4.9 | 17/6 – 21/6 | Deadline:   1. 19/6 morning: student presentations 2. 19/6 afternoon: best projects presentation and demo market |

Please note, in case there are any conflicts between this document and Context project guideline, or planning presented on black board the context project guideline and information on blackboard is leading